## Summary
Brandio — Project Status Analysis
Generated from source-code review. Status: Real/Done = built & working · Partial = works with caveats · Fake = dummy data · Missing/Blocker = not built / must-fix.
Feature / Area | Status | Notes | Key file(s)
Core AI generation (backgrounds, templates, captions) | Real | Google Gemini 2.5; multi-step pipeline with gradient fallback | background_engine/services/geminiService.js
Social publishing — Instagram / Facebook | Real | Live Meta Graph API calls | auto_poster/services/platforms/metaService.js
Social publishing — Twitter / X | Real | Live media upload + v2 /tweets | auto_poster/services/platforms/twitterService.js
Social publishing — LinkedIn | Real | Live /ugcPosts + asset upload | auto_poster/services/platforms/linkedinService.js
OAuth (all 3 platforms) | Real | Token exchange + refresh; AES-256-GCM encrypted storage | auto_poster/services/tokenService.js
Scheduler | Real | cron every minute; publishes due posts automatically | auto_poster/services/schedulerService.js
Template editor UI | Done | Full canvas editor, fonts, placeholders | post_generator/public/js/editor.js
Docker / Cloud Run packaging | Done | Dockerfile (non-root, healthcheck), compose, build.sh | Dockerfile / docker-compose.yml
JWT signature verification | Done | PHASE 1: HS256 verify + signJwt helper (Node crypto, no new deps) | shared/middleware/auth.js
CORS lockdown | Done | PHASE 1: env-driven via CORS_ORIGINS (permissive only if unset) | shared/config/corsOptions.js
Startup secret validation | Done | PHASE 1: warns in dev, exits in prod if secrets missing | shared/config/validateEnv.js
OAuth redirect URIs | Done | PHASE 1: ngrok hardcode removed; derived from PUBLIC_BASE_URL | shared/config/platforms.js
Dead placeholder OAuth route | Done | PHASE 1: removed (real flow lives in oauthRoutes.js) | auto_poster/routes/socialRoutes.js
Secrets in git history | Done | VERIFIED NOT AN ISSUE: .env never committed, properly gitignored | .gitignore
Database (SQLite migration) | Done | PHASE 2: now SQLite (node:sqlite) w/ WAL; 389 rows migrated; same API; data.json kept as backup | shared/db/database.js
User authentication / login | Done | PHASE 1.5: scrypt signup/login, JWT, login UI, token auto-attach, per-user isolation + ownership checks | manager/routes/authRoutes.js
Analytics / reporting | Done | PHASE 3: analytics API (summary/posts/refresh) + dashboard UI + platform getInsights + ownership; live data needs connected accounts | auto_poster/routes/analyticsRoutes.js + manager/public/analytics.html
Automated tests | Done | PHASE 4: 26 tests via node:test (password, JWT, auth-middleware regression, SQLite, CORS); npm test green | tests/
Observability (Sentry/uptime/alerts) | Partial | PHASE 4: structured JSON error logging on all 4 services + optional Sentry (set SENTRY_DSN); uptime/alerts need external tooling | shared/observability.js
Cross-service ownership (authz depth) | Done | Lenient ownership guard on post_gen + auto_poster business routes; enforces for logged-in users, skips internal/dev | shared/middleware/ownership.js
Input validation | Done | Dependency-free validateBody; applied to template create; covered by tests | shared/middleware/validate.js
Best-time-to-post | Fake | Returns hardcoded times, not real data | auto_poster/routes/calendarRoutes.js:145
Excel bulk import | Missing | 'Coming soon'; only CSV supported | post_generator/public/home.html:1669
Retry failed generation | Missing | 'Coming soon' | post_generator/public/js/generate.js:3131
WhatsApp posting | Missing | Placeholder for future | shared/config/platforms.js:86
Multi-user / teams / approval flow | Missing | Single shared demo user; no roles or approval | —

## What's Done
What's Already Built (and Real)
The creative engine and the real social-publishing pipeline are genuinely implemented — not mocked.
Feature | Status | Notes | Key file(s)
AI background generation | Real | Gemini gemini-2.5-flash-image; gradient fallback if image gen fails | background_engine/services/geminiService.js
AI template generation (text-to-template) | Real | JSON schema enforced; retry w/ simplified fallback | background_engine/routes/backgroundRoutes.js
AI complete template (concept->image->vision->layout) | Real | Multi-model pipeline, business branding injected | geminiService.js (~1119-2281)
Instagram / Facebook publishing | Real | Media container + publish; returns real post IDs/URLs | metaService.js
Twitter / X publishing | Real | INIT/APPEND/FINALIZE media upload + /tweets | twitterService.js
LinkedIn publishing | Real | registerUpload + /ugcPosts | linkedinService.js
OAuth — Meta | Real | Authorize, callback, long-lived token exchange | auto_poster/routes/oauthRoutes.js
OAuth — Twitter (PKCE) | Real | code_verifier/challenge; access+refresh tokens | oauthRoutes.js / twitterService.js
OAuth — LinkedIn | Real | OpenID Connect user info + token refresh | oauthRoutes.js / linkedinService.js
Token encryption | Real | AES-256-GCM, PBKDF2, salts, auth tags | auto_poster/services/tokenService.js
Scheduler | Real | cron('* * * * *'); processes due jobs, refreshes tokens | schedulerService.js / publishingService.js
Template editor | Done | Canvas, fonts, placeholders, image cropping | post_generator/public/js/editor.js
Cross-service wiring (this session) | Done | Shared service-config.js mounted + included; manager port fixed to 3004 | shared/public/service-config.js
Docker / Cloud Run / build | Done | Multi-stage Dockerfile, compose volumes, pkg build.sh | Dockerfile / build.sh
Docs | Partial | README + DEPLOYMENT.md + background_engine/api.md (no 'done vs planned' section) | README.md

## What's Left
What's Left To Build / Fix
Grouped by area. Priority: P0/Blocker = before any real users. Status column tracks progress (Phase 1 security hardening complete).
Area | Item | Priority | Problem | What to do / outcome | Location | Status
Security | No real authentication | Blocker | Every request hardcoded user_demo_001 -> all users shared data | DONE: scrypt signup/login, JWT (7d), login/signup UI, token auto-attach, per-user isolation + business-ownership checks; first signup claims demo data | manager/routes/authRoutes.js + shared/auth/password.js | DONE (Phase 1.5)
Security | Secrets committed to git | Blocker | Claimed exposure of keys in git history | VERIFIED FALSE: .env was never committed and is gitignored | .gitignore | DONE - not an issue
Security | JWT signature not verified | P0 Critical | Middleware only decoded + checked expiry | HS256 signature verify + signJwt helper added (Node crypto) | shared/middleware/auth.js | DONE (Phase 1)
Security | Dev-mode auth bypass | P0 Critical | Non-production lets ANY request through as valid | Kept dev fallback by design; tighten with real login in Phase 2 | auth.js:31-32 | PENDING (Phase 2)
Security | CORS open to all origins | P1 High | app.use(cors()) on all 4 services | Now env-driven: set CORS_ORIGINS to lock down; permissive only if unset | shared/config/corsOptions.js | DONE (Phase 1)
Data | JSON flat-file database | P0 Critical | 25MB data.json, sync read/write, no locking -> corruption | Migrated to SQLite (node:sqlite) with WAL; identical API; 389 rows imported; data.json kept as backup | shared/db/database.js + migrate-json-to-sqlite.js | DONE (Phase 2)
Data | SQLite schema is dead code | P2 Medium | init.js built SQLite then exited; runtime used JSON | Runtime now self-creates the SQLite schema; init.js superseded | shared/db/database.js | DONE (Phase 2)
Data | No input validation | P1 High | Endpoints trusted client input | DONE: dependency-free validateBody middleware + tests; applied to template create (extend to remaining write routes as needed) | shared/middleware/validate.js | DONE (Phase 4)
Security | Cross-service object ownership | P1 High | Proxied services didn't verify business_id belongs to the user | DONE: lenient requireBusinessOwnership guard on post_gen + auto_poster business routes (+ tests); enforces for logged-in users, skips internal/dev | shared/middleware/ownership.js | DONE (Phase 4)
Config | OAuth redirect URIs hardcoded to ngrok | P1 High | Defaults pointed at a personal ngrok URL | ngrok removed; redirect URIs derived from PUBLIC_BASE_URL | shared/config/platforms.js | DONE (Phase 1)
Config | No startup secret validation | P2 Medium | Missing secrets silently fall back to dev mode | validateEnv() added: warns in dev, exits in prod | shared/config/validateEnv.js | DONE (Phase 1)
Marketing | Analytics dashboard | P1 High | Table+methods existed; no API, no fetch, no UI | DONE (scaffolding): /api/analytics summary+posts+refresh, dashboard UI with empty states, platform getInsights (IG/FB/Twitter) + ownership + tests. Live numbers need connected accounts with valid tokens | auto_poster/routes/analyticsRoutes.js + analytics.html | DONE (Phase 3)
Marketing | Best-time-to-post is fake | P2 Medium | Returned hardcoded times | DONE: computed from the business's published-post history per platform, with general recommendations where data is sparse | auto_poster/routes/calendarRoutes.js | DONE (Phase 4)
Marketing | Excel bulk import missing | P3 Low | 'Coming soon'; CSV only | Add xlsx parsing (e.g. SheetJS) | post_generator/public/home.html:1669 | PENDING (Phase 3)
Marketing | Retry failed generation missing | P3 Low | 'Coming soon' toast | Implement retry handler | post_generator/public/js/generate.js:3131 | PENDING (Phase 3)
Marketing | Multi-user / teams / approval | P2 Medium | Single shared user; no roles or approval flow | Add accounts, roles, approve-before-publish | — | PENDING (Phase 3)
Marketing | WhatsApp posting | P3 Low | Placeholder only | Integrate WhatsApp Business API (or drop from UI) | shared/config/platforms.js:86 | PENDING (Phase 3)
Quality | No automated tests | P1 High | 0% coverage, no jest/mocha | DONE: 26 tests via Node built-in node:test (npm test) covering password hashing, JWT, auth-middleware regression, SQLite layer, CORS | tests/ + package.json | DONE (Phase 4)
Quality | Observability (errors/uptime/alerts) | P1 High | No Sentry, uptime checks, or alerts (Gate 12 other half) | Add error tracking + uptime pings on /health + log alerts (needs external tooling/DSN) | (pending) | PENDING (Phase 4)
Quality | Dead placeholder OAuth route | P3 Low | socialRoutes returned mock JSON (shadowed by real route) | Removed | auto_poster/routes/socialRoutes.js | DONE (Phase 1)

## Roadmap
Suggested Roadmap
Phased plan. Effort estimates are rough, single-developer.
Phase | Task | Priority | Rough effort | Status
Phase 1 — Security (do immediately) | Rotate secrets / purge git history | P0 Critical | ~1 day | DONE - verified not needed (.env never committed)
Phase 1 — Security (do immediately) | Verified JWT signatures + signJwt helper | P0 Critical | ~0.5 day | DONE
Phase 1 — Security (do immediately) | Lock down CORS (env-driven CORS_ORIGINS) | P1 High | ~0.5 day | DONE
Phase 1 — Security (do immediately) | Startup secret validation + remove ngrok/dead route | P1 High | ~0.5 day | DONE
Phase 1.5 — Real auth | Real signup/login + scrypt + per-user isolation + login UI | P0 Critical | ~3-5 days | DONE
Phase 2 — Production hardening | Swap JSON file -> SQLite + migration (WAL, same API) | P0 Critical | ~3-5 days | DONE
Phase 2 — Production hardening | OAuth redirect URIs from env (prod domain) | P1 High | ~0.5 day | Not started
Phase 2 — Production hardening | Input validation + startup secret checks | P1 High | ~2 days | Not started
Phase 3 — Marketing value | Analytics: API + dashboard + platform getInsights (scaffolded) | P1 High | ~1-2 weeks | DONE (live numbers need connected accounts)
Phase 3 — Marketing value | Excel import, retry, best-time from real data | P2 Medium | ~3-5 days | Not started
Phase 3 — Marketing value | Team / multi-client accounts + approval workflow | P2 Medium | ~1-2 weeks | Not started
Phase 4 — Confidence | Automated test suite (node:test) — 26 tests green | P1 High | ~1 week | DONE (initial suite)
Phase 4 — Confidence | Observability: structured error logging (all 4 svcs) + optional Sentry | P1 High | ~3-5 days | PARTIAL (code done; uptime/alerts/DSN = your tooling)
Tip: set the Status column to track progress (Not started / In progress / Done).